## Project Schedule
Tasks | Outline Level | Predecessors | Duration (days) | Start Date | Finish Date | Assigned To (Role) | Number of Resources | Effort (Hrs) | % Complete | Rate Per Hour | Total Cost | Status | Comments
Beat the Clock Project Schedule |  |  | 102 | 2025-10-01 | 2026-02-28 | [5 empty] | 21046 |  | 25%
1.0 PROJECT MANAGEMENT |  | 27 | 10/01/25 | 2025-10-01 | [6 empty] | 2541
1.1 Conduct Requirements Analysis | 1 |  | 3 | 2025-10-01 | 2025-10-03 | PM, ID, SME | 3 | 36 |  |  | 1596 | Not Started | PM (53), ID (37), SME (43)
1.1.1 Review Project Charter and requirements documentation | 2 | 2 | 1 | 2025-10-04 | 2025-10-04 | PM, ID | 1 | 12 | 0 | 45 | 540 | Not Started | Blended rate of PM (53) + ID (37) = 45/hr.
1.1.2 Conduct requirements definition meeting with stakeholders | 2 | 3 | 1 | 2025-10-05 | 2025-10-05 | PM, ID, SME, Stakeholders | 2 | 12 | 0 | 44 | 528 | Not Started | Blended rate of PM (53) + ID (37) + SME (43) = 44/hr. Stakeholder time not costed.
1.1.3 Draft and obtain approval for the required document | 2 | 4 | 1 | 2025-10-06 | 2025-10-06 | PM, ID, SME | 1 | 12 | 0 | 44 | 528 | Not Started | Blended rate of PM (53) + ID (37) + SME (43) = 44/hr.
1.2 Kick-off Meeting | 1 | 5 | 1 | 2025-10-07 | 2025-10-07 | PM, ID, Stakeholders | 4 | 21 |  |  | 945 | Not Started | Blended rate of PM + ID = 45/hr. Stakeholder time not costed.
1.2.1 Introduce the project and project plan to the team | 2 | 6 | 0.5 | 2025-10-08 | 2025-10-07 | PM, ID | 2 | 10 | 0 | 45 | 450 | Not Started | Blended rate of PM (53) + ID (37) = 45/hr.
1.2.2 Introduce team leaders and teams | 2 | 7 | 0.5 | 2025-10-08 | 2025-10-07 | PM, ID | 2 | 11 | 0 | 45 | 495 | Not Started | Blended rate of PM (53) + ID (37) = 45/hr.
2.0 ANALYSIS PHASE |  |  |  | 2025-10-08 | [6 empty] | 3016
2.1 Learner, Context, and Task Analysis | 1 |  | 4 | 2025-10-08 | 2025-10-11 | ID, SME | 2 | 41 |  |  | 1517 | Not Started | Blended rate of ID (37) + SME (43) = 40/hr. Both roles contribute equally.
2.1.1 Identify the target audience and their needs | 2 | 9 | 2 | 2025-10-12 | 2025-10-13 | ID | 1 | 20 | 0 | 37 | 740 | Not Started | Primary role's rate
2.1.2 Analyze project context and learning objectives | 2 | 10 | 2 | 2025-10-14 | 2025-10-15 | ID | 1 | 21 | 0 | 37 | 777 | Not Started | Primary role's rate
2.2 Review Analysis Document | 1 | 11 | 2 | 2025-10-16 | 2025-10-15 | PM, ID, SME | 3 | 31 |  |  | 1499 | Not Started
2.2.1 Review document with project team and SME | 2 | 12 | 1 | 2025-10-16 | 2025-10-15 | Team + SME | 2 | 16 | 0 | 44 | 704 | Not Started | Blended PM (53) + ID (37) + SME (43) = 44/hr.
2.2.2 Make revisions and obtain sign-off | 2 | 13 | 1 | 2025-10-16 | 2025-10-15 | PM | 1 | 15 | 0 | 53 | 795 | Not Started | Primary role's rate
3.0 DESIGN PHASE |  |  |  | 2025-10-16 | [6 empty] | 6540
3.1 Design Document Creation | 1 |  | 4 | 2025-10-16 | 2025-10-19 | ID, PM | 2 | 41 |  |  | 2614 | Not Started | ID (37) PM (53) and Graphics (27)
3.1.1 Develop goals and objectives for the module | 2 | 15 | 2 | 2025-10-20 | 2025-10-21 | ID | 1 | 20 | 0 | 37 | 740 | Not Started | Primary role's rate
3.1.2 Define gamification elements, UI, avatars, and scenarios | 2 | 16 | 2 | 2025-10-22 | 2025-10-23 | ID, Graphics | 2 | 21 | 0 | 64 | 1344 | Not Started | Primary roles' rate
3.1.3 Obtain approval for course design and outline | 2 | 17 | 1 | 2025-10-24 | 2025-10-24 | PM | 1 | 10 | 0 | 53 | 530 | Not Started | Primary role's rate
3.2 Storyboard and Script Development | 1 | 18 | 5 | 2025-10-25 | 2025-10-29 | ID, Editor | 2 | 52 |  |  | 1897 | Not Started | ID (37) and Editor (35)
3.2.1 Create detailed storyboard for scenarios and branching logic | 2 | 19 | 2 | 2025-10-30 | 2025-10-31 | ID | 1 | 18 | 0 | 37 | 666 | Not Started | Primary role's rate
3.2.2 Draft course scripts and storyboards | 2 | 20 | 2 | 2025-11-01 | 2025-11-02 | ID | 1 | 17 | 0 | 37 | 629 | Not Started | Primary role's rate
3.2.3 Review scripts with Editor | 2 | 21 | 1 | 2025-11-03 | 2025-11-03 | Editor | 1 | 10 | 0 | 35 | 350 | Not Started | Primary role's rate
3.2.4 Revise storyboard and scripts based on feedback | 2 | 22 | 1 | 2025-11-04 | 2025-11-04 | ID, Editor | 2 | 7 | 0 | 36 | 252 | Not Started | Blended rate of ID (37) + Editor (35) = 36/hr.
3.3 Visual Assets Creation | 1 | 23 | 7 | 2025-11-05 | 2025-11-11 | Graphic Designer | 1 | 36 |  |  | 1180 | Not Started | PM (53) Graphics (27)
3.3.1 Develop UI elements, avatars, and gamification badges | 2 | 24 | 3 | 2025-11-12 | 2025-11-14 | Graphic Designer | 1 | 18 | 0 | 27 | 486 | Not Started | Primary role's rate
3.3.2 Design visual templates and scenarios | 2 | 25 | 2 | 2025-11-15 | 2025-11-16 | Graphic Designer | 1 | 10 | 0 | 27 | 270 | Not Started | Primary role's rate
3.3.3 Obtain approval from stakeholders for visual assets | 2 | 26 | 2 | 2025-11-17 | 2025-11-18 | PM | 1 | 8 | 0 | 53 | 424 | Not Started | Primary role's rate
3.4 Finalize Design | 1 | 27 | 2 | 2025-11-19 | 2025-11-20 | ID, Editor | 2 | 21 |  |  | 849 | Not Started | ID (37); Editor (35)
3.4.1 Conduct SME review of the design document and storyboards | 2 | 28 | 1 | 2025-11-21 | 2025-11-21 | SME | 1 | 12 | 0 | 43 | 516 | Not Started | Primary role's rate
3.4.2 Make final revisions and obtain sign-off | 2 | 29 | 1 | 2025-11-22 | 2025-11-22 | ID | 1 | 9 | 0 | 37 | 333 | Not Started | Primary role's rate
4.0 DEVELOPMENT PHASE |  |  |  | 2025-12-01 | [6 empty] | 6074
4.1 Alpha and Beta Development | 1 |  | 8 | 2025-12-01 | 2025-12-08 | Developers, ID | 2 | 83 |  |  | 3763 | Not Started | Developer (43) ID (37)
4.1.1 Create an alpha version of the course in Storyline | 2 | 31 | 3 | 2025-12-09 | 2025-12-11 | Technical Lead | 1 | 30 | 0 | 53 | 1590 | Not Started | TL-53 Primary role's rate
4.1.2 Conduct alpha review and make revisions for beta version | 2 | 32 | 2 | 2025-12-12 | 2025-12-13 | Team | 2 | 25 | 0 | 41 | 1025 | Not Started | Blended team rate calculated from PM (53), ID (37), SME (43), Graphics (27), Editor (35), Developer (43), LMS Integrator (43), QA Lead (44), QA Tester (41). Average = 41/hr.
4.1.3 Conduct beta review and make final revisions | 2 | 33 | 2 | 2025-12-14 | 2025-12-15 | Team | 2 | 28 | 0 | 41 | 1148 | Not Started | Blended team rate calculated from PM (53), ID (37), SME (43), Graphics (27), Editor (35), Developer (43), LMS Integrator (43), QA Lead (44), QA Tester (41). Average = 41/hr.
4.1.4 Conduct beta review with stakeholders | 2 | 34 | 1 | 2025-12-16 | 2025-12-16 | Stakeholders | 2 | 20 | 0 | 0 | 0 | Not Started | Stakeholder time not costed.
4.2 Pilot Test | 1 | 35 | 3 | 2025-12-17 | 2025-12-19 | QA, PM | 2 | 31 |  |  | 1451 | Not Started | QA (41) PM (53)
4.2.1 Select pilot testers and gather feedback | 2 | 36 | 1 | 2025-12-20 | 2025-12-20 | PM | 1 | 15 | 0 | 53 | 795 | Not Started | Primary role's rate
4.2.2 Modify course based on feedback | 2 | 37 | 2 | 2025-12-21 | 2025-12-22 | Team | 2 | 16 | 0 | 41 | 656 | Not Started | Blended team rate calculated from PM (53), ID (37), SME (43), Graphics (27), Editor (35), Developer (43), LMS Integrator (43), QA Lead (44), QA Tester (41). Average = 41/hr.
4.3 Quality Assurance (QA) | 1 | 38 | 3 | 2025-12-23 | 2025-12-25 | QA Lead, QA Tester | 2 | 31 |  |  | 860 | Not Started | QA Lead (44) QA Tester (41)
4.3.1 Conduct QA review in LMS test environment | 2 | 39 | 2 | 2025-12-26 | 2025-12-27 | QA Team | 2 | 20 | 0 | 43 | 860 | Not Started | Blended rate of QA Lead (44) + QA Tester (41) = 43/hr.
4.3.2 Obtain sign-off and approval for implementation | 2 | 40 | 1 | 2025-12-28 | 2025-12-28 | Stakeholders | 2 | 11 | 0 | 0 | 0 | Not Started | Stakeholder time not costed.
5.0 IMPLEMENTATION PHASE |  |  |  | 2026-01-16 | [6 empty] | 1906
5.1 Course Deployment | 1 |  | 1 | 2026-01-16 | 2026-01-16 | LMS Integrator | 1 | 8 |  |  | 424 | Not Started | LMS-53
5.1.1 Schedule and deploy the course in the production environment | 2 | 42 | 1 | 2026-01-17 | 2026-01-17 | LMS Integrator | 1 | 8 | 0 | 53 | 424 | Not Started | Primary role's rate
5.2 User Training Materials Development | 1 | 43 | 2 | 2026-01-18 | 2026-01-19 | ID, Editor | 2 | 16 | 0 | 36 | 576 | Not Started | Blended rate of ID (37) + Editor (35) = 36/hr.
5.3 Communication Plan Launch | 1 | 44 | 2 | 2026-01-20 | 2026-01-21 | PM, Communications Coordinator | 2 | 12 | 0 | 43 | 516 | Not Started | Blended rate of PM (53) + Communications Coordinator (33) = 43/hr.
5.4 Technical Support Preparation | 1 | 45 | 2 | 2026-01-22 | 2026-01-23 | QA, Support Lead | 2 | 10 | 0 | 39 | 390 | Not Started | Blended rate of QA (41) + Support Lead (36) = 39/hr.
6.0 EVALUATION PHASE | [10 empty] | 969
6.1 Evaluation & Feedback Analysis | 1 |  | 2 | 2026-02-21 | 2026-02-22 | ID | 1 | 12 |  |  | 444 | Not Started | ID (37)
6.1.1 Collect and analyze assessment results from the course | 2 | 47 | 1 | 2026-02-23 | 2026-02-23 | ID | 1 | 6 | 0 | 37 | 222 | Not Started | Primary role's rate
6.1.2 Collect feedback from learners | 2 | 48 | 1 | 2026-02-24 | 2026-02-24 | ID | 1 | 6 | 0 | 37 | 222 | Not Started | Primary role's rate
6.2 Publish Evaluation Report | 1 | 49 | 2 | 2026-02-25 | 2026-02-26 | Editor | 1 | 15 |  |  | 525 | Not Started | Editor (35)
6.2.1 Prepare and publish the final evaluation report | 2 | 50 | 2 | 2026-02-27 | 2026-02-28 | Editor | 1 | 15 | 0 | 35 | 525 | Not Started | Primary role's rate